## Project
Title: | Senior Design I - Wind Turbine Simulation (TIMELINE)
Date | Task | Days | Height | Axis | Label
2012-10-04 | Testing the old code |  | 45 | 41186 | Testing the old code
2012-09-28 | Project Plan (first version) |  | 37 | 41180 | Project Plan (first version)
2012-11-09 | Project Plan (2nd version) |  | 37 | 41222 | Project Plan (2nd version)
2012-11-29 | Project Plan (Final) |  | 37 | 41242 | Project Plan (Final)
2012-12-04 | Presentations |  | 55 | 41247 | Presentations
2012-10-25 | Testing the old hardware |  | 30 | 41207 | Testing the old hardware
2012-10-25 | New code |  | -30 | 41207 | New code
2012-10-25 | Code Simulation |  |  | 41207 | Code Simulation
2012-11-24 | Finish hardware |  |  | 41237 | Finish hardware
2012-12-24 | Hardware testing |  |  | 41267 | Hardware testing
2013-01-28 | Sumulation 1 |  |  | 41302 | Sumulation 1
2013-01-28 | Sumulation 2 |  |  | 41302 | Sumulation 2
2012-09-27 | Client meeting |  | -20 | 41179 | Client meeting
2012-10-04 | Client meeting |  | -20 | 41186 | Client meeting
2012-10-11 | Client meeting |  | -20 | 41193 | Client meeting
2012-10-18 | Client meeting |  | -20 | 41200 | Client meeting
2012-10-25 | Client meeting |  | -20 | 41207 | Client meeting
2012-11-01 | Client meeting |  | -20 | 41214 | Client meeting
2012-11-08 | Client meeting |  | -20 | 41221 | Client meeting
2012-11-15 | Finish design I |  | 20 | 41228 | Finish design I
2012-11-15 | Finish the simulation pahse IV |  | 10 | 41228 | Finish the simulation pahse IV
2012-11-15 | Order parts |  | 5 | 41228 | Order parts
2012-11-15 | Client meeting |  | -20 | 41228 | Client meeting
2012-11-22 | Client meeting |  | -20 | 41235 | Client meeting
2012-11-25 | Finish the design V |  | 10 | 41238 | Finish the design V
2012-11-29 | Client meeting |  | -20 | 41242 | Client meeting
2012-11-29 | Testing the new design |  | 15 | 41242 | Testing the new design
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Formulas:
Date = [Date, row above]
Date = [Date, row above]+30